## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Design Auth DB & Entities | Design SQL Server database schema, User and RefreshToken entities for authentication. | 1 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/1 | Closed | PhucLM | 2026-05-27 22:16 | 2026-05-28 22:38 | iter1 | Task, 3_Done | User Authentication API
Implement Login & Register APIs | Develop REST endpoints for user registration, local login, logout, and token refresh. | 2 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/2 | Closed | PhucLM | 2026-05-27 22:16 | 2026-05-29 12:42 | iter1 | Task, 3_Done | User Authentication API
Integrate Google OAuth2 | Integrate Google ID Token verification on the backend to authenticate Google Login users. | 3 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/3 | Closed | PhucLM | 2026-05-26 20:16 | 2026-05-27 22:16 | iter1 | Task, 3_Done | User Authentication API
Implement Upgrade Requests | Create UpgradeRequest entity and endpoints for spectators to submit role upgrades. | 4 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/4 | Closed | PhucLM | 2026-05-28 14:29 | 2026-05-29 16:29 | iter1 | Task, 3_Done | Upgrade Role Request API
Implement Admin Upgrade Approval | Create admin endpoints to approve or reject upgrade requests with audit logs. | 5 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/5 | Closed | PhucLM | 2026-05-28 14:29 | 2026-05-29 16:29 | iter1 | Task, 3_Done | Upgrade Role Request API
Implement Wallet Entities & APIs | Design Wallet, WalletTransaction entities, and write APIs to fetch user balance and history. | 6 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/6 | Closed | PhucLM | 2026-06-17 23:08 | 2026-06-19 01:08 | iter2 | Task, 3_Done | Wallet & Transactions API
Implement Withdrawal Workflow | Develop API to create withdrawal requests and enable admin approval workflow. | 7 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/7 | Closed | PhucLM | 2026-06-17 23:08 | 2026-06-19 01:08 | iter2 | Task, 3_Done | Wallet & Transactions API
Implement Jockey Connections | Write Jockey profile queries and connections API to friend and partner with horse owners. | 8 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/8 | Closed | PhucLM | 2026-06-16 11:00 | 2026-06-17 13:00 | iter2 | Task, 3_Done | Jockey Connection API
AI Chat Assistant Integration | Integrate Google Gemini API to retrieve context-aware answers to user inquiries. | 9 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/9 | Closed | PhucLM | 2026-06-16 09:56 | 2026-06-19 08:16 | iter2 | Task, 3_Done | AI Chat Assistant API
Implement Breed Management | Write API to CRUD horse breeds for administrative system configurations. | 10 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/10 | Closed | PhucLM | 2026-06-19 15:33 | 2026-06-20 17:33 | iter2 | Task, 3_Done | Breed Management API
Implement Tournament Admin Controls | Develop endpoints to schedule tournaments, register tracks, and allocate referee users. | 11 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/11 | Closed | PhucLM | 2026-06-21 22:39 | 2026-07-02 17:37 | iter3 | Task, 3_Done | Tournament & Track API
Implement Pre-race Inspection | Create API for referees to weigh jockeys, check tracks, and update inspection status. | 12 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/12 | Closed | PhucLM | 2026-06-21 22:39 | 2026-07-05 15:41 | iter3 | Task, 3_Done | Referee Controls API
Implement Referee Flags & Penalties | Create API for referees to add penalty flags and log horse fouls during active races. | 13 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/13 | Closed | PhucLM | 2026-06-21 11:00 | 2026-06-22 13:00 | iter3 | Task, 3_Done | Referee Controls API
Develop Race Simulation Engine | Implement backend scheduling to update horse position, speed, and stamina during live simulation. | 14 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/14 | Closed | PhucLM | 2026-07-04 13:41 | 2026-07-05 15:41 | iter3 | Task, 3_Done | Live Race Simulation API
Implement Public Simulation Polling | Create public API for clients to retrieve active race positions and leaderboard via polling. | 15 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/15 | Closed | PhucLM | 2026-07-02 17:37 | 2026-07-04 14:45 | iter3 | Task, 3_Done | Live Race Simulation API
PayOS Payment Integration | Develop endpoints to create transaction links via PayOS SDK integration. | 16 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/16 | Closed | PhucLM | 2026-07-06 11:00 | 2026-07-07 13:00 | iter4 | Task, 3_Done | PayOS Payment Gateway API
PayOS Webhook Handler | Create secure public endpoint to receive and verify PayOS webhook signatures to fund wallets. | 17 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/17 | Closed | PhucLM | 2026-07-13 08:20 | 2026-07-14 10:20 | iter4 | Task, 3_Done | PayOS Payment Gateway API
Implement Betting Validation & Place | Create endpoints to place Win/Place/Show bets with user balance and race state validations. | 18 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/18 | Closed | PhucLM | 2026-07-06 11:00 | 2026-07-07 13:00 | iter4 | Task, 3_Done | Spectator Betting API
Pari-Mutuel Odds & Payout Logic | Implement Pari-Mutuel dynamic odds algorithm and automated prize payouts on race completion. | 19 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/19 | Closed | PhucLM | 2026-07-13 12:20 | 2026-07-14 14:20 | iter4 | Task, 3_Done | Spectator Betting API
Implement Admin Dashboard API | Create analytics endpoints returning total platform revenue, transaction history, and upgrade stats. | 20 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/20 | Closed | PhucLM | 2026-07-06 11:00 | 2026-07-07 13:00 | iter4 | Task, 3_Done | Admin Dashboard API
Implement Excel/PDF Export Services | Implement file exports for tournament scores, financial receipts, and PDF invoices. | 21 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/21 | Closed | PhucLM | 2026-07-06 11:00 | 2026-07-07 13:00 | iter4 | Task, 3_Done | Report Exporting API
Implement User Profile Services | Develop API to fetch/update user profile details, upload avatar files, and change passwords. | 22 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/22 | Closed | PhucLM | 2026-07-17 11:20 | 2026-07-18 13:20 | iter4 | Task, 3_Done | User Profile API
Implement Bank Account & Withdrawal Snapshot API | Add bank details in User profile. Snapshot bank details on withdrawal requests. Add cancel API for pending withdrawals. | 23 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/23 | Closed | PhucLM | 2026-07-18 14:00 | 2026-07-18 18:00 | iter4 | Task, 3_Done | Wallet & Transactions API, User Profile API
Profile Bank Editing, Custom Modals & UX Formatters | Add bank name and account inputs in all user profiles. Implement custom system confirmation/alert modals for withdrawal. Enforce bank details on withdrawal, format input amounts with commas, and prevent digit overflows. | 24 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/24 | Closed | PhucLM | 2026-07-18 15:00 | 2026-07-18 18:00 | iter4 | Task, 3_Done | Wallet & Transactions API, User Profile API, Frontend Wallet UI
Replace Referee with Track Shape in Tournament Registration | In the Horse Owner registration dashboard, hide the referee name field and display the track shape (Straight/Circular) instead. | 25 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/25 | Closed | PhucLM | 2026-07-18 16:13 | 2026-07-18 16:13 | iter4 | Task, 3_Done | Tournament Registration, Frontend Horse Owner Dashboard
Implement Full-Stack Feedback Management System | Develop feedback entities, APIs for user submission and admin resolution, header modal UI, admin feedback management panel, and database initializer seeds. | 26 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/26 | Closed | PhucLM | 2026-07-19 05:00 | 2026-07-19 12:23 | iter4 | Task, 3_Done | Feedback Management API, Admin Feedbacks Panel
Implement Automated Prediction Payout Service & Unit Tests | Develop PredictionPayoutService for automated payout calculations and referee result processing with unit test coverage. | 27 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/27 | Closed | PhucLM | 2026-07-17 13:00 | 2026-07-19 11:57 | iter4 | Task, 3_Done | Spectator Betting API
Enhance Admin Tournaments Management & Backend Service | Refactor tournament service handling, update admin tournament management panel UI, and improve error response handling. | 28 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/28 | Closed | PhucLM | 2026-07-18 14:00 | 2026-07-18 16:08 | iter4 | Task, 3_Done | Tournament & Track API, Admin Tournaments Panel
Implement Admin Blacklist Management System | Develop AdminBlacklistService and AdminBlacklistController endpoints for listing, adding, and unbanning users/horses with ban history auditing, status restoration, system alerts, and frontend BlacklistPanel UI integration. | 29 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/29 | Closed | PhucLM | 2026-07-19 12:30 | 2026-07-19 12:35 | iter4 | Task, 3_Done | Admin Blacklist Management API, Admin Blacklist Panel
Admin Dashboard Real-Data Analytics & Extended Charts | Aggregate 4 new real-data metrics in AdminDashboardController (Horse Breeds, Race Statuses, Deposit vs Withdrawal Trends, Top Tournament Prizes) and build 4 Recharts components in AdminDashboardContent. | 30 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/30 | Closed | PhucLM | 2026-07-19 12:42 | 2026-07-19 12:45 | iter4 | Task, 3_Done | Admin Dashboard API, Admin Dashboard Content
Implement Notification Mark All As Read Feature | Integrate markAllAsReadAPI (PUT /api/notifications/read-all) in DashboardHeader notification dropdown allowing users to mark all notifications as read at once. | 31 | https://github.com/MinhPhuc00ne/horse-racing-system/issues/31 | Closed | PhucLM | 2026-07-19 12:45 | 2026-07-19 12:46 | iter4 | Task, 3_Done | Notification API, DashboardHeader