## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | User Authentication API | Registration, Login (Local & Google OAuth2), Logout, Token Refresh, Password Reset | Guest, Spectator, User | Manages user authentication workflows, including registration, secure login with local credentials or Google OAuth2, session logout, JWT security verification, and token rotation for security. | PhucLM | Done | iter1 | none
2 | Upgrade Role Request API | Submit Upgrade Request, Admin Review (Approve/Reject) | Spectator, Admin | Enables spectators to submit role upgrade requests to become horse owners or jockeys. Provides endpoints for administrators to review, approve, or reject these requests with custom feedback. | PhucLM | Done | iter1 | none
3 | Wallet & Transactions API | View Balance, Request Withdrawal, Admin Withdrawal Approval, Cancel Withdrawal (Snapshot details), Profile Default Bank Account, Custom Alerts & Formatters | All Roles, Admin | Provides wallet balance inquiries and records transaction histories. Supports user withdrawal requests and allows administrators to review and approve transactions. | PhucLM | Done | iter4 | iter4 | Added default bank details to user profile, transaction snapshot, cancellation API, and custom wallet alerts/comma formatters.
4 | Jockey Connection API | Friend Request, Accept/Reject Connection, View Friend List | Horse Owner, Jockey | Facilitates pairing and social connections between horse owners and jockeys. Supports searching for jockeys, sending requests, and accepting/rejecting invitations for tournament collaboration. | PhucLM | Done | iter2 | none
5 | AI Chat Assistant API | Send Prompt, Get Role-Based Suggestions, Fetch Conversation History | All Roles | Integrates Google Gemini API to offer interactive AI assistance. Provides tailored advice on race rules, system usage, and strategies based on the user's role with thread tracking. | PhucLM | Done | iter2 | none
6 | Breed Management API | Create Breed, Retrieve Breed List | Admin, Horse Owner | Allows administrators to register and manage horse breeds in the system, which are used as scheduling constraints and filters for tournament eligibility. | PhucLM | Done | iter2 | none
7 | Tournament & Track API | Create Tournament, Configure Race Rewards, Manage Tracks, Assign Referees, Replace Referee with Track Shape in Owner Registration | Admin | Administrative API for organizing tournaments, scheduling races, setting up cash rewards for top 3 positions, setting rules, registering tracks, and assigning referees. | PhucLM | Done | iter3 | iter4 | Replaced referee name display with track shape (Straight/Circular) in Horse Owner registration cards.
8 | Referee Controls API | Pre-race Inspection, Flag Violation, Control Race State (Start/Pause/Stop) | Race Referee | Enables referees to record pre-race jockey weights and track inspections, flag participant violations, issue penalty cards, and control the live race simulation sequence. | PhucLM | Done | iter3 | none
9 | Live Race Simulation API | Stream Real-Time Coordinates, Get Active Leaderboards | All Roles, Guest | Exposes live racing coordinates, horse velocities, stamina depletion, and referee flags through periodic polling endpoints to render the real-time simulation screen. | PhucLM | Done | iter3 | none
10 | PayOS Payment Gateway API | Create Deposit Invoice Link, Handle PayOS Webhook, Verify Transaction | All Roles | Integrates the PayOS payment gateway. Automates user wallet balance increments upon receiving signed webhooks confirming successful bank transfer deposits. | PhucLM | Done | iter4 | none
11 | Spectator Betting API | Place Win/Place/Show Bets, Pari-Mutuel Odds Computation, Bet Refund | Spectator | Manages spectator betting tickets. Calculates dynamic odds using the Pari-Mutuel pool-sharing algorithm and distributes rewards on referee results confirmation. Handles refunds if races are cancelled. | PhucLM | Done | iter4 | none
12 | Admin Dashboard API | Aggregate Revenue, Compile System Statistics, User Activity Logs | Admin | Compiles platform financial reports, total active users, transaction volumes, and recent activity logs to aid overall system monitoring. | PhucLM | Done | iter4 | iter4 | Aggregated 4 new real-data datasets (Horse Breeds, Race Statuses, Deposit/Withdraw Trends, Top Tournament Prizes) for extended Recharts components.
13 | Report Exporting API | Export Tournament Excel, Export Financial Statements, Generate Invoices | Admin, Horse Owner | Exports tournament brackets, betting history, platform revenue sheets, and individual transaction details in Excel or PDF formats using JasperReports/Apache POI. | PhucLM | Done | iter4 | none
14 | User Profile API | Fetch Profile, Update Personal Details, Change Password, Upload Avatar, Save Bank Details | All Roles | Provides endpoints for users to manage their profiles, update contact details, upload profile pictures, and securely update passwords. | PhucLM | Done | iter4 | iter4 | Added default bank account details (bank name, bin, account number, holder name) to profile.
15 | Admin Blacklist Management API | List Blacklists, Ban User/Horse, Unban & Restore Status | Admin | Provides backend services and endpoints for Administrators to query blacklists, ban users or horses, unban targets to restore account/horse status, log ban history, and dispatch system notifications. | PhucLM | Done | iter4 | iter4 | Implemented AdminBlacklistService, AdminBlacklistController, BlacklistResponse DTO, ban_history auditing, and frontend BlacklistPanel UI.
16 | Notification API | Get Notifications, Unread Count, Mark Single as Read, Mark All as Read | All Roles | Manages user notifications for system alerts, feedback resolutions, upgrade approvals, and invitations. Supports marking individual notifications or all notifications as read. | PhucLM | Done | iter4 | iter4 | Added Mark All As Read (PUT /api/notifications/read-all) button integration in DashboardHeader notification dropdown.

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | User Authentication API | Registration, Login (Local & Google OAuth2), Logout, Token Refresh, Password Reset | Manages user authentication workflows, including registration, secure login with local credentials or Google OAuth2, session logout, JWT security verification, and token rotation for security. | PhucLM | Done | II.1 | III.1 | Configured Spring Security and database connection.
2 | Upgrade Role Request API | Submit Upgrade Request, Admin Review (Approve/Reject) | Enables spectators to submit role upgrade requests to become horse owners or jockeys. Provides endpoints for administrators to review, approve, or reject these requests with custom feedback. | PhucLM | Done | II.2 | III.2 | Admin upgrade workflow completed.
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Wallet & Transactions API | View Balance, Request Withdrawal, Admin Withdrawal Approval | Provides wallet balance inquiries and records transaction histories. Supports user withdrawal requests and allows administrators to review and approve transactions. | PhucLM | Done | III.1 | IV.1 | Mock deposits and wallet balances working.
2 | Jockey Connection API | Friend Request, Accept/Reject Connection, View Friend List | Facilitates pairing and social connections between horse owners and jockeys. Supports searching for jockeys, sending requests, and accepting/rejecting invitations for tournament collaboration. | PhucLM | Done | III.2 | IV.2 | Owner-Jockey connection rules enforced.
3 | AI Chat Assistant API | Send Prompt, Get Role-Based Suggestions, Fetch Conversation History | Integrates Google Gemini API to offer interactive AI assistance. Provides tailored advice on race rules, system usage, and strategies based on the user's role with thread tracking. | PhucLM | Done | III.3 | IV.3 | Optimized prompt templates for Google Gemini.
4 | Breed Management API | Create Breed, Retrieve Breed List | Allows administrators to register and manage horse breeds in the system, which are used as scheduling constraints and filters for tournament eligibility. | PhucLM | Done | III.4 | IV.4 | Admin breed control active.
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Tournament & Track API | Create Tournament, Configure Race Rewards, Manage Tracks, Assign Referees | Administrative API for organizing tournaments, scheduling races, setting up cash rewards for top 3 positions, setting rules, registering tracks, and assigning referees. | PhucLM | Done | IV.1 | V.1 | Added track conflict detection and scheduling checks.
2 | Referee Controls API | Pre-race Inspection, Flag Violation, Control Race State (Start/Pause/Stop) | Enables referees to record pre-race jockey weights and track inspections, flag participant violations, issue penalty cards, and control the live race simulation sequence. | PhucLM | Done | IV.2 | V.2 | Referees inspect and penalize horses live.
3 | Live Race Simulation API | Stream Real-Time Coordinates, Get Active Leaderboards | Exposes live racing coordinates, horse velocities, stamina depletion, and referee flags through periodic polling endpoints to render the real-time simulation screen. | PhucLM | Done | IV.3 | V.3 | Background simulation engine updates positions every second.
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | PayOS Payment Gateway API | Create Deposit Invoice Link, Handle PayOS Webhook, Verify Transaction | Integrates the PayOS payment gateway. Automates user wallet balance increments upon receiving signed webhooks confirming successful bank transfer deposits. | PhucLM | Done | V.1 | VI.1 | Integrated PayOS payment check with signature security.
2 | Spectator Betting API | Place Win/Place/Show Bets, Pari-Mutuel Odds Computation, Bet Refund | Manages spectator betting tickets. Calculates dynamic odds using the Pari-Mutuel pool-sharing algorithm and distributes rewards on referee results confirmation. Handles refunds if races are cancelled. | PhucLM | Done | V.2 | VI.2 | Dynamic pool betting calculations completed.
3 | Admin Dashboard API | Aggregate Revenue, Compile System Statistics, User Activity Logs | Compiles platform financial reports, total active users, transaction volumes, and recent activity logs to aid overall system monitoring. | PhucLM | Done | V.3 | VI.3 | Analytics dashboards integrated for Admins.
4 | Report Exporting API | Export Tournament Excel, Export Financial Statements, Generate Invoices | Exports tournament brackets, betting history, platform revenue sheets, and individual transaction details in Excel or PDF formats using JasperReports/Apache POI. | PhucLM | Done | V.4 | VI.4 | Supported offline Excel and PDF invoice exports.
5 | User Profile API | Fetch Profile, Update Personal Details, Change Password, Upload Avatar | Provides endpoints for users to manage their profiles, update contact details, upload profile pictures, and securely update passwords. | PhucLM | Done | V.5 | VI.5 | Profile details and secure password updates.
6 | Wallet & Transactions API | Request Withdrawal, Cancel Withdrawal, Default Bank Details, Custom Alert Modals, Comma Input Formatters | Enables users to request and cancel withdrawals. Stores bank details snapshot directly in the transaction record. | PhucLM | Done | III.1 | IV.1 | Added default bank details, transaction snapshot, cancellation API, and custom wallet alerts/comma formatters.
7 | Tournament & Track API | Display Track Shape in Owner Registration | Replace referee name display with track shape (Straight/Circular) on tournament cards. | PhucLM | Done | IV.1 | V.1 | Replaced referee name with track shape in Horse Owner dashboard for registration.
8 | Feedback Management API | Submit Feedback, Admin Review & Resolution, Seed Data | Full-stack feedback management allowing users to submit system feedback with ratings/categories, header modal integration, admin panel to review/resolve/reject with notes, and database initialization seed data. | PhucLM | Done | V.6 | VI.6 | Integrated Send Feedback header modal, Admin Feedbacks Panel, API endpoints, and DatabaseInitializer seeds.
9 | Spectator Betting & Payout API | Prediction Payout Processing & Unit Test Suite | Developed PredictionPayoutService for automated payout calculations and referee result processing, along with comprehensive JUnit test suite. | PhucLM | Done | V.2 | VI.2 | PredictionPayoutService implementation and test coverage.
10 | Tournament & Track API | Admin Tournaments Management & Service Optimizations | Enhanced Admin Tournaments management UI panel, updated backend TournamentService logic, and global exception handling. | PhucLM | Done | IV.1 | V.1 | Refactored tournament management backend logic and updated frontend TournamentsPanel.
11 | Admin Blacklist Management API | List Blacklists, Ban User/Horse, Unban & Restore Status | Provides backend services and endpoints for Administrators to query blacklists, ban users or horses, unban targets to restore account/horse status, log ban history, and dispatch system notifications. | PhucLM | Done | V.7 | VI.7 | Implemented AdminBlacklistService, AdminBlacklistController, BlacklistResponse DTO, ban_history auditing, and frontend BlacklistPanel UI.
12 | Admin Dashboard API | Real-Data Extended Charts & Metrics | Aggregated 4 new real-data datasets in AdminDashboardController for Horse Breeds, Race Statuses, Deposit vs Withdraw Trends, and Top Tournament Prizes. | PhucLM | Done | V.3 | VI.3 | Added 4 new real-data chart components (BreedPieChart, RaceStatusBarChart, TransactionTrendChart, TournamentPrizeChart) to AdminDashboardContent.
13 | Notification API | Mark All Notifications As Read | Added Mark All As Read API integration in DashboardHeader notification dropdown to clear all pending notifications in one click. | PhucLM | Done | V.8 | VI.8 | Integrated markAllAsReadAPI (PUT /api/notifications/read-all) in DashboardHeader header button.
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document